## Cover Page
APQC Project Status Report

## Live Projects
Sr. No. | Proposal Code | Custom/SOW/RS/Internal/Advisory | Project Name | APQC POC | Start Date | End Date | Current Stage | Immediate Next Milestone | Ownership | Target # of Submissions | Achieved # of Submissions Till Date | Remaining # of Submissions | Dependencies on APQC | Open Items
1 | PPPAA-305 | Custom | 2025 Custom Finance Study | Jonathan Kraft | 2025-06-05 | 2025-09-30 | Completed | None | Phronesis | 70 | 70 | 0 | None | Awaiting feedback on final deliverable
2 | PPPAA-317 | Custom | 2025 SG&A Study | Jonathan Kraft | 2025-07-17 | 2025-12-16 | In-field | Share interim deliverable on 6th November | Phronesis | 70 | 24 | 46 | None | None
3 | PPPAA-262_1 | SOW | AI in Thought Leadership Consumer Study | Jonathan Kraft | 2025-07-30 | 2025-09-25 | Completed | None | Phronesis | 1000 | 1000 | 0 | None | Awaiting feedback on final deliverable
4 | PPPAA-262 | SOW | AI in Thought Leadership Producer Study | Jonathan Kraft | 2025-08-06 | 2025-11-06 | In-field | Share final deliverable on 30th October | Phronesis | 350 | 205 | 145 | None | None | 8 completes
5 | PPPAA-319 | Internal | Bounty Hunter - Sales and Marketing | Jonathan Kraft | 2025-08-18 | 2025-10-10 | Completed | None | Phronesis | 268 | 268 | 0 | None | Awaiting feedback on final deliverable
6 | PPPAA-282 | SOW | HR Organization Study | Jonathan Kraft | 2025-08-20 | 2025-10-24 | Completed | None | Phronesis | 1218 | 1218 | 0 | None | Awaiting feedback on final deliverable
7 | PPPAA-247 | SOW | 2025 Customer Strategy Study | Jonathan Kraft | 2025-09-24 | TBD | Set-Up | Launch fieldwork | Phronesis | 1330 | 0 | 1330 | None | Awaiting feedback on test link
8 | PPPAA-333 | Internal | Bounty Hunter Survey - Planning and Logistics | Jonathan Kraft | 2025-10-10 | 2025-12-05 | In-field | Share pilot deliverable on 4th November | Phronesis | 268 | 0 | 268 | None | None
9 | PPPAA-338 | RS | SCM 2026 Priorities and Challenges Survey | Benjamin Knoll | 2025-10-07 | 2025-11-28 | Set-Up | Launch fieldwork on 3rd November | Phronesis | 300 | 0 | 300 | None | None
9.1 | PPPAA-338 | RS | SCM 2026 Priorities and Challenges Survey | Benjamin Knoll | 2025-10-07 | 2025-12-05 | Set-Up | Launch fieldwork on 3rd November | APQC |  | 0 | 0 | None | None
10 | PPPAA-339 | RS | FM 2026 Priorities and Challenges Survey | Benjamin Knoll | 2025-10-07 | 2025-11-28 | Set-Up | Launch fieldwork on 3rd November | Phronesis | 300 | 0 | 300 | None | None
10.1 | PPPAA-339 | RS | FM 2026 Priorities and Challenges Survey | Benjamin Knoll | 2025-10-07 | 2025-12-06 | Set-Up | Launch fieldwork on 3rd November | Phronesis |  | 0 | 0 | None | None | Final link for the FM survey for internal clients

## Projects Yet to be Started
Sr. No. | Proposal Code | Custom/SOW/RS/Internal | Project Name | APQC POC | Current Stage | Immediate Next Milestone | Target # of Submissions | Dependencies on APQC | Open Items
1 | PPPAA-292 | Custom | Bundle Project - 4 | Jonathan Kraft |  |  | 75 |  |  | This year | SPG early next week
2 | PPPAA-292 | Custom | Bundle Project - 5 | Jonathan Kraft |  |  | 75 |  |  | This year
3 | PPPAA-292 | Custom | Bundle Project - 6 | Jonathan Kraft |  |  | 75 |  |  | Next year
4 | PPPAA-292 | Custom | Bundle Project - 7 | Jonathan Kraft |  |  | 75 |  |  | Next year
5 | PPPAA-296 | SOW | 2025 Cloud Modernization Study | Jonathan Kraft |  |  | 1025 |  |  | Q2' 2026
6 | PPPAA-297 | SOW | Sales and Commerce Study | Jonathan Kraft |  |  | 1025 |  |  | Q4' 2025 or Q1' 2026
7 | PPPAA-298 | SOW | Application Development | Jonathan Kraft |  |  | 1282
8 | PPPAA-299 | SOW | Asset Management - Industrial | Jonathan Kraft |  |  | 609 |  |  | Q2' 2026
9 | PPPAA-300 | SOW | Asset Management - Real Estates | Jonathan Kraft |  |  | 608 |  |  | Q2' 2026
10 | PPPAA-302 | SOW | Talent Acquisition | Jonathan Kraft |  |  | 1025 |  |  | Q1' 2026
11 | PPPAA-309 | SOW | Field Service Study | Jonathan Kraft |  |  | 1025
12 | PPPAA-314 | SOW | 2025 Data Services AI Study | Jonathan Kraft |  |  | 1025 |  |  | December or February
13 | PPPAA-259 | SOW | 2024 Sales Performance Survey - B2B Focused | Jonathan Kraft |  |  | 1025 |  |  | Q4' 2025 or Q1' 2026
14 | PPPAA-330 | SOW | Accounts Payable and Expenses Study | Jonathan Kraft |  |  | 700
15 | PPPAA-331 | SOW | Business Application Management | Jonathan Kraft |  |  | 1025
16 | PPPAA-332 | SOW | AI Impact in Finance | Jonathan Kraft |  |  | 1025

## Upcoming Projects
Sr. No. | Proposal Code | APQC POC | Custom/SOW/RS/Internal | Project Name | SOW Submission Date | n= | Current Status/Last Comment
1 | NA | Jonathan Kraft | SOW | Functional Headcount and Cost Benchmarking | 2025-02-14 | 1000 | Shared assessment, awaiting confirmation from APQC | Main phase to be confirmed
2 | NA | Jonathan Kraft | Custom | HR Metrics in Retail | 2025-03-12 | 20 | Shared assessment, awaiting confirmation from APQC | Cathy is working on this
3 | PPPAA-289 | Jonathan Kraft | Custom | Custom Procurement Study | 2025-03-26 | Op1: 800 Op2: 400 | Shared assessment, awaiting confirmation from APQC | In discussion with the client
4 | PPPAA-290 | Jonathan Kraft | Custom | Custom Product Test Assemble Study | 2025-03-26 | Op1: 264 Op2: 132 | Shared assessment, awaiting confirmation from APQC | In discussion with the client
5 | PPPAA-291 | Jonathan Kraft | Custom | Custom Supply Chain Study | 2025-03-26 | Op1: 264 Op2: 132 | Shared assessment, awaiting confirmation from APQC | In discussion with the client
6 | PPPAA-321 | Jonathan Kraft | Custom | Custom Functional Pricing (study across 9 functions) | 2025-07-01 | 90 | Shared assessment, awaiting confirmation from APQC
7 | PPPAA-322 | Jonathan Kraft | Custom | Custom Retail Supply Chain study | 2025-07-08 | Option 1: 3 European countries with an N of 6 for each and 6 for each of the following: US, Canada, ANZ, China, Japan, and Korea for a total of 54 Option 2: 6 from Europe as a whole region and 6 from each of the following: US, Canada, ANZ, China, Japan, and Korea for a total of 42 | Shared assessment, awaiting confirmation from APQC
8 | NA | Jonathan Kraft | Custom | Small Custom Study - Banking | 2025-07-31 | 15 | Shared assessment, awaiting confirmation from APQC
9 | PPPAA-325 | Jonathan Kraft | Custom | Custom- Justice Department Finance Study | 2025-08-22 | 4 | Shared assessment, awaiting confirmation from APQC | Sent to client for signature
10 | PPPAA-328 | Jonathan Kraft | Custom | Custom Top of Mind-Tariff Study | 2025-09-01 | Option 1:250 Option 2:600 | Shared assessment, awaiting confirmation from APQC | In discussion with the client
11 | PPAA-329 | Jonathan Kraft | Custom | Category Spend Benchmarks | 2025-09-10 | 35 | Shared assessment, awaiting confirmation from APQC
12 | PPPAA-334 | Jonathan Kraft | Custom | Custom Project - Telecom Study | 2025-09-22 | 80 | Shared assessment, awaiting confirmation from APQC
13 | PPPAA-335 | Jonathan Kraft | Custom | RE: Custom Study - Utilities (same group as the telecom study) | 2025-09-24 | 30 | Shared assessment, awaiting confirmation from APQC
14 | PPPAA-336 | Jonathan Kraft | Custom | RE: Custom Study - Manufacturing (same group as the telecom study) | 2025-09-24 | 30 | Shared assessment, awaiting confirmation from APQC
15 | PPPAA-337 | Jonathan Kraft | Custom | Custom AI Study | 2025-10-03 | TBF | Shared assessment, awaiting confirmation from APQC
16 | PPPAA-341 | Jonathan Kraft | Custom | Custom Private Banking Clients and Wealth Management Clients | 2025-10-17 | 15 | Shared assessment, awaiting confirmation from APQC
17 | PPPAA-340 | Jonathan Kraft | Custom | Custom Pharma Pricing [Repeat client] | 2025-10-22 | 30 | Shared assessment, awaiting confirmation from APQC

## Deliverable Status
Sr. No. | Custom/SOW/RS/Internal/Advisory | Project Name | Phronesis PM | Deliverable Stage | Due Date | Delivered On | EST Delivery Time | Status | Status | %
1 | Internal | Bounty Hunter Survey FM (General Accounting and Reporting and AP) | Vishal Talwar | Interim | 2025-05-13 | 2025-05-09 | 7:00 | N-2 (Before Due Date) | Ontime (or before due date) | 74.42%
2 | SOW | 2025 Supply Chain Planning | Vishal Talwar | Pilot | 2025-05-12 | 2025-05-12 | 13:26 | Delayed | Delayed (or after due date) | 25.58%
3 | Custom | 2025 Marketing for Life Sciences Study | Ravi Sharma | Pilot | 2025-05-14 | 2025-05-13 | 14:30 | N-1 (Before Due Date)
4 | Custom | HR Shared Services Study 2025 | Vishal Talwar | Interim | 2025-05-20 | 2025-05-20 | 7:30 | On Time
5 | SOW | 2025 Talent Management Study | Vishal Talwar | Interim | 2025-05-22 | 2025-05-22 | 6:30 | On Time
6 | Custom | 2025 Marketing for Life Sciences Study | Ravi Sharma | Interim | 2025-05-22 | 2025-05-22 | 12:05 | Delayed
7 | Internal | Bounty Hunter Survey FM (General Accounting and Reporting and AP) | Vishal Talwar | Final | 2025-05-23 | 2025-05-23 | 7:00 | On Time
8 | SOW | Generative AI Impact Study | Vishal Talwar | Interim | 2025-05-27 | 2025-05-27 | 13:28 | Delayed
9 | Custom | HR Shared Services Study 2025 | Vishal Talwar | Final | 2025-05-28 | 2025-05-28 | 9:25 | On Time
10 | Internal | 2025 Marketing for Life Sciences Study | Ravi Sharma | Final | 2025-05-28 | 2025-05-28 | 7:07 | On Time
11 | SOW | Generative AI Impact Study | Vishal Talwar | Interim | 2025-05-27 | 2025-05-27 | 13:28 | Delayed
12 | Custom | HR Shared Services Study 2025 | Vishal Talwar | Final | 2025-05-28 | 2025-05-28 | 9:25 | On Time
13 | Custom | 2025 Marketing for Life Sciences Study | Ravi Sharma | Final | 2025-05-28 | 2025-05-28 | 7:07 | On Time
14 | RS | Cash Flow Practices Study | Diksha Srivastava | Interim | 2025-05-28 | 2025-05-28 | 9:07 | On Time
15 | Custom | Bundle 1 - 2025 Customer Service Management | Vishal Talwar | Pilot | 2025-05-29 | 2025-05-29 | 8:50 | On Time
16 | RS | Cash Flow Practices Study | Manmeet Kapoor | Final | 2025-06-04 | 2025-06-04 | 11:45 | Delayed
17 | RS | SCM Analytics and Data Management Study | Manmeet Kapoor | Pilot | 2025-06-05 | 2025-06-05 | 14:50 | Delayed
18 | Custom | Bundle 1 - 2025 Customer Service Management | Vishal Talwar | Interim | 2025-06-10 | 2025-06-10 | 7:35 | On Time
19 | SOW | 2025 Talent Management Study | Vishal Talwar | Final | 2025-06-11 | 2025-06-11 | 9:02 | On Time
20 | RS | 2025 Performance Management | Manmeet Kapoor | Pilot | 2025-06-13 | 2025-06-13 | 8:15 | On Time
21 | RS | 2025 Performance Management | Manmeet Kapoor | Pilot | 2025-06-13 | 2025-06-13 | 8:15 | On Time
22 | RS | SCM Analytics and Data Management Study | Manmeet Kapoor | Interim | 2025-06-16 | 2025-06-16 | 9:45 | On Time
23 | Custom | 2025 Custom Supply Chain Study | Ravi Sharma | Pilot | 2025-06-16 | 2025-06-16 | 11:15 | Delayed
24 | SOW | 2025 Supply Chain Planning | Vishal Talwar | Interim | 2025-06-18 | 2025-06-18 | 11:08 | Delayed
25 | Custom | Bundle 1 - 2025 Customer Service Management | Vishal Talwar | Final | 2025-06-19 | 2025-06-19 | 7:00 | On Time
26 | RS | SCM Analytics and Data Management Study | Manmeet Kapoor | Final | 2025-06-20 | 2025-06-20 | 10:27 | On Time
27 | SOW | 2025 Cross Functional Benchmarks Study (Pilot) | Ravi Sharma | Pilot | 2025-06-23 | 2025-06-23 | 8:58 | On Time
28 | RS | 2025 Performance Management | Manmeet Kapoor | Interim | 2025-06-24 | 2025-06-24 | 11:45 | Delayed
29 | RS | Strategic Planning and Organizational Ability | Shivangi Bhasin | Pilot | 2025-06-24 | 2025-06-24 | 10:09 | On Time
30 | RS | Procure to Pay 2025 | Manmeet Kapoor | Pilot | 2025-06-24 | 2025-06-24 | 10:55 | On Time
31 | SOW | 2025 Finance Organization Study | Vishal Talwar | Pilot | 2025-06-26 | 2025-06-26 | 7:33 | On Time
32 | SOW | Generative AI Impact Study | Vishal Talwar | Final | 2025-06-27 | 2025-06-27 | 9:32 | On Time
33 | Custom | 2025 Product Innovation OEM Automotive Study | Ravi Sharma | Pilot | 2025-06-30 | 2025-06-30 | 10:02 | On Time
34 | Custom | 2025 Custom Supply Chain Study | Ravi Sharma | Interim | 2025-07-01 | 2025-07-01 | 9:05 | On Time
35 | RS | 2025 Performance Management | Manmeet Kapoor | Final | 2025-07-01 | 2025-07-01 | 11:28 | Delayed
36 | SOW | 2025 Cross Functional Benchmarks Study (Pilot) | Ravi Sharma | Interim | 2025-07-02 | 2025-07-02 | 6:49 | On Time
37 | Custom | 2025 KM Retirement Planning Study | Vishal Talwar | Pilot | 2025-07-02 | 2025-07-02 | 9:34 | On Time
38 | RS | Procure to Pay 2025 | Manmeet Kapoor | Interim | 2025-07-02 | 2025-07-02 | 14:52 | Delayed
39 | Internal | Bounty Hunter-HCM Recruiting, Onboard, and Employee Analytics Study | Vishal Talwar | Pilot | 2025-07-03 | 2025-07-03 | 10:39 | On Time
40 | RS | Strategic Planning and Organizational Ability | Shivangi Bhasin | Interim | 2025-07-03 | 2025-07-03 | 8:28 | On Time
41 | Custom | 2025 Custom Supply Chain Study | Ravi Sharma | Final | 2025-07-08 | 2025-07-08 | 8:55 | On Time
42 | SOW | 2025 Finance Organization Study | Vishal Talwar | Interim | 2025-07-08 | 2025-07-08 | 12:44 | Delayed
43 | SOW | 2025 Supply Chain Planning | Vishal Talwar | Final | 2025-07-09 | 2025-07-09 | 10:00 | On Time
44 | SOW | 2025 Cross Functional Benchmarks Study (Pilot) | Ravi Sharma | Final | 2025-07-09 | 2025-07-09 | 10:55 | On Time
45 | RS | Procure to Pay 2025 | Manmeet Kapoor | Final | 2025-07-10 | 2025-07-10 | 8:56 | On Time
46 | RS | Strategic Planning and Organizational Ability | Shivangi Bhasin | Final | 2025-07-11 | 2025-07-11 | 12:32 | Delayed
47 | Custom | 2025 Product Innovation OEM Automotive Study | Ravi Sharma | Interim | 2025-07-16 | 2025-07-16 | 9:13 | On Time
48 | Custom | 2025 KM Retirement Planning Study | Vishal Talwar | Interim | 2025-07-18 | 2025-07-18 | 10:46 | On Time
49 | SOW | 2025 Finance Organization Study | Vishal Talwar | Interim | 2025-07-22 | 2025-07-22 | 11:01 | On Time
50 | Internal | Bounty Hunter-HCM Recruiting, Onboard, and Employee Analytics Study | Vishal Talwar | Interim | 2025-07-23 | 2025-07-23 | 12:07 | Delayed
51 | Custom | Bundle 2 - 2025 Field Service Management | Vishal Talwar | Pilot | 2025-07-23 | 2025-07-23 | 8:43 | On Time
52 | Custom | 2025 Product Innovation OEM Automotive Study | Ravi Sharma | Final | 2025-07-24 | 2025-07-24 | 12:25 | Delayed
53 | Custom | 2025 Custom Finance Study | Vishal Talwar | Pilot | 2025-07-25 | 2025-07-28 | 8:45 | On Time
54 | Custom | 2025 KM Retirement Planning Study | Vishal Talwar | Final | 2025-07-30 | 2025-07-30 | 9:33 | On Time
55 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Pilot | 2025-08-05 | 2025-08-05 | 10:55 | On Time
56 | Internal | Bounty Hunter-HCM Recruiting, Onboard, and Employee Analytics Study | Vishal Talwar | Final | 2025-08-06 | 2025-08-06 | 10:51 | On Time
57 | Custom | Bundle 2 - 2025 Field Service Management | Vishal Talwar | Interim | 2025-08-07 | 2025-08-07 | 9:31 | On Time
58 | SOW | 2025 Finance Organization Study | Vishal Talwar | Final | 2025-08-08 | 2025-08-08 | 10:58 | On Time
59 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-08-14 | 2025-08-14 | 10:59 | On Time
60 | Custom | Bundle 2 - 2025 Field Service Management | Vishal Talwar | Final | 2025-08-18 | 2025-08-18 | 10:33 | On Time
61 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-08-20 | 2025-08-20 | 10:34 | On Time
62 | SOW | AI in Thought Leadership Consumer Study | Vishal Talwar | Pilot | 2025-08-22 | 2025-08-22 | 12:18 | Delayed
63 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-08-27 | 2025-08-27 | 10:40 | On Time
64 | Custom | 2025 Custom Finance Study | Vishal Talwar | Interim | 2025-09-02 | 2025-09-02 | 16:46 | Delayed
65 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-09-03 | 2025-09-03 | 9:32 | On Time
66 | Custom | 2025 SG&A Study | Vishal Talwar | Pilot | 2025-09-04 | 2025-09-04 | 10:58 | On Time
67 | Internal | Bounty Hunter - Sales and Marketing | Vishal Talwar | Pilot | 2025-09-09 | 2025-09-09 | 8:38 | On Time
68 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-09-09 | 2025-09-09 | 9:34 | On Time
69 | Custom | Bundle 3 - 2025 Strategic Portfolio Management | Vishal Talwar | Pilot | 2025-09-10 | 2025-09-10 | 10:06 | On Time
70 | SOW | HR Organization Study | Vishal Talwar | Pilot | 2025-09-11 | 2025-09-11 | 10:59 | On Time
71 | SOW | AI in Thought Leadership Consumer Study | Vishal Talwar | Interim | 2025-09-15 | 2025-09-15 | 10:43 | On Time
72 | RS | Knowledge and Process Productivity | Manmeet Kapoor | Pilot | 2025-09-16 | 2025-09-16 | 9:22 | On Time
73 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Interim | 2025-09-16 | 2025-09-16 | 10:44 | On Time
74 | SOW | AI in Thought Leadership Producer Study | Ravi Sharma | Pilot | 2025-09-17 | 2025-09-17 | 12:18 | Delayed
75 | Custom | 2025 Custom Tax Survey Extension | Vishal Talwar | Final | 2025-09-24 | 2025-09-24 | 6:32 | On Time
76 | Custom | Bundle 3 - 2025 Strategic Portfolio Management | Vishal Talwar | Interim | 2025-09-24 | 2025-09-24 | 7:33 | On Time
77 | Internal | Bounty Hunter - Sales and Marketing | Vishal Talwar | Interim | 2025-09-25 | 2025-09-25 | 10:57 | On Time
78 | SOW | AI in Thought Leadership Consumer Study | Vishal Talwar | Final | 2025-09-25 | 2025-09-25 | 13:09 | Delayed
79 | Custom | 2025 Custom Finance Study | Vishal Talwar | Final | 2025-09-30 | 2025-10-01 | 9:25 | Delayed
80 | SOW | HR Organization Study | Vishal Talwar | Interim | 2025-10-01 | 2025-10-01 | 10:58 | On Time
81 | Custom | Bundle 3 - 2025 Strategic Portfolio Management | Vishal Talwar | Final | 2025-10-01 | 2025-10-01 | 10:30 | On Time
82 | RS | Knowledge and Process Productivity | Diksha Srivastava | Final | 2025-10-03 | 2025-10-03 | 7:10 | On Time
83 | Internal | Bounty Hunter - Sales and Marketing | Vishal Talwar | Final | 2025-10-10 | 2025-10-10 | 9:44 | On Time
84 | SOW | AI in Thought Leadership Producer Study | Ravi Sharma | Interim | 2025-10-14 | 2025-10-14 | 12:40 | Delayed
85 | SOW | HR Organization Study | Vishal Talwar | Final | 2025-10-24 | 2025-10-24 | 10:34 | On Time
0 | SOW | AI in Thought Leadership Producer Study | Ravi Sharma | Interim | 2025-10-24 | 2025-10-25 | 10:31 | Delayed

## Closed Projects
Sr. No. | Proposal Code | Custom/SOW | Project Name | APQC POC | Start Date | End Date | Current Stage | Target # of Submissions | Achieved # of Submissions Till Date
1 | PPPAA-264 | Internal | Bounty Hunter Survey - Reward and Retain | Jonathan Kraft | 2024-10-21 | 2024-12-19 | Completed | 275 | 275
2 | PPPAA-237 | SOW | 2024 Procurement Study | Jonathan Kraft | 2024-09-16 | 2024-12-20 | Completed | 1250 | 1250
3 | PPPAA-205 | Custom | Bundle Functional Leadership Projects-Project-7-2024 Legal Management | Jonathan Kraft | 2024-11-01 | 2024-12-16 | Completed | 75 | 75
4 | PPPAA-270 | RS | Onboarding Study | Benjamin Knoll | 2024-12-04 | 2025-01-17 | Completed | 300 | 316
5 | PPPAA-275 | Advisory | Innovation in Banks - Pilot Phase | Matthew Zacher | 2024-12-02 | 2025-01-17 | Completed | 3 | 3
6 | PPPAA-244 | SOW | AI in Customer Service | Jonathan Kraft | 2024-10-23 | 2025-01-14 | Completed | 740 | 740
7 | PPPAA-232 | SOW | Product Development Study | Jonathan Kraft | 2024-11-18 | 2025-01-28 | Completed | 1000 | 1000
8 | PPPAA-205 | Custom | Bundle Functional Leadership Projects-Project-8 and 9-Integrated Risk Management | Jonathan Kraft | 2024-12-03 | 2025-01-31 | Completed | 150 | 150
9 |  | Internal | Product Development Study | Jonathan Kraft | 2024-11-14 | 2025-02-14 | Completed | 2500 | 2500
10 | PPPAA-205 | Custom | Bundle Functional Leadership Projects-Project-10-IT Service Management | Jonathan Kraft | 2024-12-11 | 2025-02-17 | Completed | 75 | 75
11 |  | Internal | Big Data - ESG - II | Jonathan Kraft | 2024-11-11 | 2025-02-28 | Completed | 2500 | 2500
12 | PPPAA-269 | RS | HR Function Blueprint Study | Jonathan Kraft | 2024-12-06 | 2025-02-21 | Completed | 300 | 300
13 | PPPAA-253 | Advisory | Inspection Programs Benchmarking Study | Matthew Zacher | 2025-01-23 | 2025-02-26 | Completed | 12 | 12
14 | PPPAA-225 | Custom | 2025 Custom Tax Survey | Jonathan Kraft | 2025-01-21 | 2025-03-17 | Completed | 400 | 403
15 | PPPAA-203 | SOW | 2024 IT Risk & Security Survey | Jonathan Kraft | 2024-12-11 | 2025-03-21 | Completed | 1300 | 1300
16 | PPPAA-224 | SOW | IT Organization | Jonathan Kraft | 2024-12-11 | 2025-03-27 | Completed | 1320 | 1320
17 | PPPAA-279 | Custom | Police Departments Study | Jonathan Kraft | 2025-02-12 | 2025-03-24 | Completed | 6 | 6
18 | PPPAA-268 | Internal | Bounty Hunter Survey - 2024 IT General Organization | Jonathan Kraft | 2025-01-06 | 2025-04-02 | Completed | 275 | 275
19 | PPPAA-275 | Advisory | Innovation in Banks | Matthew Zacher | 2025-01-23 | 2025-04-10 | Completed | 17 | 17
20 | PPPAA-273 | SOW | 2025 Financial Planning & Analysis | Jonathan Kraft | 2025-02-07 | 2025-04-16 | Completed | 1240 | 1240
21 | PPPAA-285 | Custom | 2025 Product Innovation Study | Jonathan Kraft | 2025-03-17 | 2025-05-05 | Completed | 25 | 25
22 | PPPAA-286 | Internal | Bounty Hunter Survey FM (General Accounting and Reporting and AP) | Jonathan Kraft | 2025-03-25 | 2025-05-23 | Completed | 268 | 268
23 | PPPAA-260 | SOW | 2024 Marketing Performance Survey | Jonathan Kraft | 2025-01-31 | 2025-05-02 | Completed | 1060 | 1060
24 | PPPAA-272 | SOW | AI in Marketing Study | Jonathan Kraft | 2025-01-31 | 2025-05-06 | Completed | 740 | 740
25 | PPPAA-288 | Custom | 2025 Marketing for Life Sciences Study | Jonathan Kraft | 2025-04-29 | 2025-05-28 | Completed | 15 | 15
26 | PPPAA-293 | RS | Cash Flow Practices Study | Benjamin Knoll | 2025-04-21 | 2025-06-04 | Completed | 300 | 316
27 | PPPAA-274 | SOW | 2025 Talent Management Study | Jonathan Kraft | 2025-04-04 | 2025-06-11 | Completed | 1240 | 1240
28 | PPPAA-295 | RS | SCM Analytics and Data Management Study | Benjamin Knoll | 2025-05-08 | 2025-06-20 | Completed | 300 | 315
29 | PPPAA-292 | Custom | Bundle 1 - 2025 Customer Service Management | Jonathan Kraft | 2025-05-14 | 2025-06-19 | Completed | 75 | 75
30 | PPPAA-278 | SOW | HR Shared Services Study 2025 | Jonathan Kraft | 2025-03-28 | 2025-05-28 | Completed | 100 | 100
31 | PPPAA-256 | SOW | Generative AI Impact Study | Jonathan Kraft | 2025-02-20 | 2025-06-27 | Completed | 1967 | 1967
32 | PPPAA-280 | Custom | 2025 Custom Supply Chain Study | Jonathan Kraft | 2025-05-29 | 2025-07-08 | Completed | 12 | 12
33 | PPPAA-301 | SOW | 2025 Cross Functional Benchmarks Study (Pilot) | Jonathan Kraft | 2025-06-05 | 2025-07-09 | Completed | 6 | 6
34 | PPPAA-310 | RS | Strategic Planning and Organizational Ability | Benjamin Knoll | 2025-06-03 | 2025-07-11 | Completed | 300 | 308
34.1 | PPPAA-310 | RS | Strategic Planning and Organizational Ability | Benjamin Knoll | 2025-06-03 | 2025-07-21 | Completed |  | 242
35 | PPPAA-303 | RS | 2025 Performance Management | Benjamin Knoll | 2025-05-23 | 2025-07-01 | Completed | 300 | 312
36 | PPPAA-311 | RS | Procure to Pay 2025 | Benjamin Knoll | 2025-06-04 | 2025-07-10 | Completed | 300 | 304
37 | PPPAA-284 | SOW | 2025 Supply Chain Planning | Jonathan Kraft | 2025-04-14 | 2025-07-09 | Completed | 1602 | 1602
38 | PPPAA-313 | Custom | 2025 Product Innovation OEM Automotive Study | Jonathan Kraft | 2025-06-05 | 2025-07-22 | Completed | 10 | 10
29 | PPPAA-283 | Custom | 2025 KM Retirement Planning Study | Jonathan Kraft | 2025-06-09 | 2025-07-30 | Completed | 1000 | 1000
30 | PPPAA-316 | Internal | Bounty Hunter-HCM Recruiting, Onboard, and Employee Analytics Study | Jonathan Kraft | 2025-06-11 | 2025-08-06 | Completed | 268 | 268
31 | PPPAA-281 | SOW | 2025 Finance Organization Study | Jonathan Kraft | 2025-05-29 | 2025-08-08 | Completed | 1218 | 1218
32 | PPPAA-292 | Custom | Bundle 2 - 2025 Field Service Management | Jonathan Kraft | 2025-07-07 | 2025-08-18 | Completed | 75 | 75
33 | PPPAA-225 | Custom | 2025 Custom Tax Survey Extension | Jonathan Kraft | 2025-07-21 | 2025-09-24 | Completed | 200 | 200
34 | PPPAA-292 | Custom | Bundle 3 - 2025 Strategic Portfolio Management | Jonathan Kraft | 2025-08-28 | 2025-10-01 | Completed | 75 | 75
35 | PPPAA-324 | RS | Knowledge and Process Productivity | Benjamin Knoll | 2025-08-15 | 2025-10-03 | Completed | 300 | 310
35.1 | PPPAA-324 | RS | Knowledge and Process Productivity | Benjamin Knoll | 2025-08-15 | 2025-10-15 | Completed |  | 367